CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

Version 0.2

– Ho Chi Minh City, September 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	6

1.3 Project Risks	7

2. Management Approach	8

2.1 Project Process	8

2.2 Quality Management	9

2.3 Training Plan	9

3. Project Deliverables	9

4. Responsibility Assignments	10

5. Project Communications	11

6. Configuration Management	11

6.1 Document Management	11

6.2 Source Code Management	11

6.3 Tools & Infrastructures	11

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 07/09/2026 | A | Nguyễn Huỳnh Nhật Anh and project team | Initial v0.1 plan aligned with the submitted Capstone Project Register and the SEP490 Student Guide milestone sequence. |
| 18/09/2026 | M | Nguyễn Huỳnh Nhật Anh and project team | Replaced the feature-group WBS with the 12 ratified major features (FE-01–FE-12) from Report 1 v0.2 for consistency across reports; added evidence-based project risks sourced from Report 1 v0.2 (LI-10, LI-08) and the engineering decision log; confirmed quality/NFR targets (LI-05, LI-06); filled in Quality Management, Training Plan, Project Communications, and Configuration Management with concrete, sourced practices; corrected the source-code repository reference. |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

This plan uses the 12 major features (FE-01–FE-12) ratified in Report 1 v0.2 (Project Introduction) as the Work Breakdown Structure baseline, so Report 1 and Report 2 stay consistent. Complexity ratings and man-day estimates are left for the team to confirm in an effort-estimation session; no fabricated numbers are included below.

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | FE-01 Authentication and Candidate Profile |  |  |
| 1.1 | FE-01.1 Register, log in, and log out. | Simple |  |
| 1.2 | FE-01.2 View and update personal profile information and account credentials. |  |  |
| 1.3 | FE-01.3 Protect Candidate and Admin functions through authentication and role-based authorization. | Medium |  |
| 2 | FE-02 Job Description Management |  |  |
| 2.1 | FE-02.1 Paste or enter JD text and upload a supported JD document. | Simple |  |
| 2.2 | FE-02.2 Extract job title, seniority indicators, domain knowledge, programming languages, frameworks, databases, tools, and other technical requirements. | Medium |  |
| 2.3 | FE-02.3 Allow the Candidate to review, correct, add, or remove extracted requirements. | Simple |  |
| 2.4 | FE-02.4 Save the reviewed JD and prevent blueprint generation until Candidate review is complete. | Simple |  |
| 2.5 | FE-02.5 Allow a Candidate to access only their own JDs. | Simple |  |
| 3 | FE-03 Interview Blueprint and Configuration |  |  |
| 3.1 | FE-03.1 Select a reviewed JD and configure difficulty, duration, question count, and optional focus areas. | Simple |  |
| 3.2 | FE-03.2 Generate a reusable interview blueprint containing coverage, stages, time allocation, question budget, expected depth, and evaluation competencies. | Medium |  |
| 3.3 | FE-03.3 Keep configured difficulty separate from seniority inferred from the JD. | Simple |  |
| 3.4 | FE-03.4 Validate that stage time and question budgets agree with the Candidate's selected configuration. | Simple |  |
| 3.5 | FE-03.5 Support non-destructive blueprint regeneration so a failed attempt does not erase a previously valid blueprint. | Medium |  |
| 4 | FE-04 AI Virtual Interview |  |  |
| 4.1 | FE-04.1 Start a one-to-one interview session from an approved and persisted blueprint. | Medium |  |
| 4.2 | FE-04.2 Ask questions and contextual follow-up questions at runtime while remaining within the blueprint's assessment boundaries. | Complex |  |
| 4.3 | FE-04.3 Maintain ordered interview turns containing interviewer questions, Candidate transcripts, and session context. | Medium |  |
| 4.4 | FE-04.4 Track completed, failed, interrupted, and active session states. | Medium |  |
| 4.5 | FE-04.5 Pause or recover gracefully when an AI or voice provider temporarily fails without corrupting completed turns. | Complex |  |
| 5 | FE-05 Voice and 3D Interviewer |  |  |
| 5.1 | FE-05.1 Capture Candidate speech through the browser microphone and convert it to text. | Medium |  |
| 5.2 | FE-05.2 Synthesize the interviewer's questions as spoken audio. | Medium |  |
| 5.3 | FE-05.3 Present a web-based 3D interviewer with synchronized speaking and lip movement. | Complex |  |
| 5.4 | FE-05.4 Provide a lower-resource audio-focused fallback when 3D rendering is unavailable or unusable. | Medium |  |
| 5.5 | FE-05.5 Display clear microphone, listening, processing, speaking, and connection states. | Simple |  |
| 6 | FE-06 Evaluation and Performance Reporting |  |  |
| 6.1 | FE-06.1 Evaluate Technical Accuracy, Depth of Understanding, Problem-Solving, Answer Relevance, and Communication Clarity. | Complex |  |
| 6.2 | FE-06.2 Ground evaluation criteria in reviewed JD expectations and Candidate-selected focus areas. | Medium |  |
| 6.3 | FE-06.3 Produce an overall score and technical-domain scores. | Medium |  |
| 6.4 | FE-06.4 Provide question-level feedback, strengths, weaknesses, and personalized improvement recommendations. | Medium |  |
| 6.5 | FE-06.5 Preserve the blueprint snapshot used by a session so a historical report remains reproducible after later configuration changes. | Simple |  |
| 7 | FE-07 Interview History |  |  |
| 7.1 | FE-07.1 List previous interviews by target JD, date, status, and overall score. | Simple |  |
| 7.2 | FE-07.2 Allow the Candidate to reopen completed reports and review session details. | Simple |  |
| 7.3 | FE-07.3 Allow repeat practice from a reusable blueprint while keeping each session and report separate. | Simple |  |
| 8 | FE-08 Subscription, Billing and Payment |  |  |
| 8.1 | FE-08.1 Show the Candidate's current subscription plan and remaining interview credits. | Simple |  |
| 8.2 | FE-08.2 Support plan upgrades or additional credit purchases through a third-party payment gateway. | Medium |  |
| 8.3 | FE-08.3 Store transaction history and payment status. | Simple |  |
| 8.4 | FE-08.4 Process payment callbacks idempotently and grant credits only after verified successful payment. | Medium |  |
| 9 | FE-09 Admin Account and Session Management |  |  |
| 9.1 | FE-09.1 View Candidate accounts and account details. | Simple |  |
| 9.2 | FE-09.2 Lock or unlock Candidate accounts. | Medium |  |
| 9.3 | FE-09.3 View and filter interview sessions by Candidate, status, or date. | Simple |  |
| 9.4 | FE-09.4 Inspect session details and monitor completed, failed, or interrupted sessions. | Medium |  |
| 10 | FE-10 Admin Interview Configuration |  |  |
| 10.1 | FE-10.1 Manage technical domains and technologies used as interview context. | Simple |  |
| 10.2 | FE-10.2 Configure allowed difficulty levels, duration constraints, evaluation criteria, and interview behaviour guidelines. | Simple |  |
| 10.3 | FE-10.3 Configure AI interview and evaluation settings without changing completed historical reports. | Simple |  |
| 11 | FE-11 Admin Avatar and Voice Management |  |  |
| 11.1 | FE-11.1 Manage available 3D virtual interviewer avatars. | Simple |  |
| 11.2 | FE-11.2 Manage supported interviewer voice profiles. | Simple |  |
| 11.3 | FE-11.3 Control which avatar and voice combinations are available to Candidates. | Simple |  |
| 12 | FE-12 Analytics, Subscription and Revenue Management |  |  |
| 12.1 | FE-12.1 View totals for active, completed, failed, and interrupted interview sessions. | Simple |  |
| 12.2 | FE-12.2 Analyse interview volume, average Candidate performance, and commonly identified technical weaknesses. | Medium |  |
| 12.3 | FE-12.3 Manage pricing plans, subscription tiers, or credit packages. | Simple |  |
| 12.4 | FE-12.4 View transaction status and revenue reports by day, month, or year. | Simple |  |
| Total Estimated Effort (man-days) |  |  |  |

### 1.2 Project Objectives

The project objective is to design, develop, and deploy RoleCue: an AI-powered virtual technical interview simulation platform that turns a target Job Description into a reviewed set of requirements, a reusable interview blueprint, a voice-based interview with a 3D virtual interviewer, and a detailed AI performance report, for the Candidate and Admin roles defined in the Capstone Project Register. The project will also produce the required SEP490 documents, source code, database scripts, test documentation, installation guidance, and a deployable software package.

Quality objectives and measurable targets:

- Common operations (login, profile viewing, interview-history retrieval, report viewing) target a response time within 3 seconds under normal test conditions (LI-05).

- AI analysis and evaluation may take longer, but must show a loading/progress indication (LI-05).

- The system targets at least 20 concurrent users under normal testing (LI-06).

- JWT-based authentication and role-based authorization between Candidate and Admin (Capstone Register NFR).

- HTTPS for all client–server communication (Capstone Register NFR).

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing |  |  |  | Mandatory pull-request review before any merge into main (applied since PR #1). |
| 2 | Unit Test |  |  |  | Go backend unit tests; frontend unit tests with Vitest. |
| 3 | Integration Test |  |  |  | Testcontainers-based backend API integration tests (KAN-41 / PR #14). |
| 4 | System Test |  |  |  | End-to-end scenarios with Playwright covering each major feature FE-01–FE-12. |
| 5 | Acceptance Test |  |  |  | Supervisor/checkpoint review against Report 1 v0.2 feature and limitation criteria (FE-01–FE-12, LI-01–LI-12). |

Milestone timeliness target:

Allocated effort distribution:

### 1.3 Project Risks

Risks below are drawn from Report 1 v0.2 (LI-08, LI-10) and the project's engineering decision log — they reflect real open technical decisions, not hypothetical scenarios. Impact/Possibility ratings are a starting assessment; the team should review and confirm before finalizing.

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Speech-to-Text / Text-to-Speech provider not yet selected (candidates: Whisper/Deepgram for STT, ElevenLabs/Azure Speech for TTS). | High | Medium | Timebox a latency/quality benchmarking spike before Code Iteration 1; select the provider behind a configurable interface so it can be swapped without redesign. |
| 2 | Production 3D avatar rendering and blend-shape lip-sync architecture is still a research spike (Three.js / @react-three/fiber prototype only). | High | Medium | Complete the lip-sync spike (SPK-03) early; rely on the audio-only fallback already defined in Report 1 v0.2 (LI-08) if 3D integration slips. |
| 3 | Payment gateway provider not yet selected (candidates: VNPay, MoMo, Stripe, PayOS). | Medium | Medium | Select the gateway early given the academic requirement for a Vietnamese gateway; isolate integration behind a payment-adapter interface; process callbacks idempotently. |
| 4 | Go PDF extraction library not yet chosen and the ingestion pipeline is unverified. | Medium | Medium | Run the planned benchmarking spike (SPK-01: pdfcpu / ledongthuc/pdf / pdftotext CLI); keep PDF text extraction isolated from LLM extraction so the choice does not affect KAN-18. |
| 5 | Jira ticket status can show "Done" while the corresponding implementation is still an open, unmerged pull request, risking an inaccurate progress picture. | Low | Medium | Report actual progress by merged-code state (not Jira status alone) in weekly reports and in the Report 2/3 update cycles. |
| 6 | Several core technical decisions (voice provider, avatar pipeline, payment gateway, PDF library) remain open while the SEP490 timeline is fixed at 15 weeks. | High | Medium | Resolve all open technical decisions by the end of Week 3 (Overall Requirement Description) so Code Iteration 1 does not start with unresolved dependencies. |

## 2. Management Approach

The team will use an iterative, milestone-based development approach aligned with the SEP490 lifecycle. Each milestone updates the relevant project documents, tracking information, implementation artefacts, and testing evidence.

### 2.1 Project Process

Process model: iterative, milestone-based delivery tracked through Jira (board "KAN").

The lifecycle is aligned with the official 15-week SEP490 sequence. Week 1 is displayed from 07/09/2026; this has been cross-checked against the official milestone table (SEP490 Student Guide) and is consistent with the current calendar date.

Official milestone sequence:

- Week 1 (07–11 Sep 2026): Project Introduction;

- Week 2 (14–18 Sep 2026): Project Plan;

- Week 3 (21–25 Sep 2026): Overall Requirement Description; update Reports 1–2 and project tracking;

- Week 5 (05–09 Oct 2026): Overall Software Design; initial test documentation; code frame; update Reports 1–3 and tracking;

- Week 7 (19–23 Oct 2026): Code Iteration 1;

- Week 9 (02–06 Nov 2026): Code Iteration 2;

- Week 11 (16–20 Nov 2026): Code Iteration 3;

- Week 13 (30 Nov–04 Dec 2026): System Testing;

- Week 14 (07–11 Dec 2026): Transition;

- Week 15 (14–18 Dec 2026): Transition.

### 2.2 Quality Management

- Quality management is evidence-based and aligned with SEP490 deliverables, maintaining traceability from requirements to design, implementation, test cases, test reports, defects, and project tracking.

- Defect Prevention: type-safe boundaries — sqlc-generated queries on the backend, Zod schema validation on the frontend — plus a standardized error/response envelope (ADR-003) for consistent, auditable failure handling.

- Reviewing: mandatory pull-request review before any merge into main, already practiced since PR #1.

- Unit Testing: Go backend unit tests; frontend unit tests with Vitest.

- Integration Testing: Testcontainers-based backend API integration tests (KAN-41, in progress).

- System Testing: end-to-end scenarios with Playwright covering each major feature (FE-01–FE-12).

Coverage targets, defect thresholds, review SLAs, and acceptance criteria remain TBD — Team confirmation.

### 2.3 Training Plan

Training needs are derived from the technologies and capability areas already registered for the project, tied to the research spikes already defined for the team.

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Go (Golang) and PostgreSQL back-end stack | All team members | Week 1–2 | Mandatory for members without prior Go/PostgreSQL experience |
| Next.js 16 / React 19 web client development | All team members | Week 1–2 | Mandatory for members without prior Next.js experience |
| LLM-based JD extraction (spike SPK-02: OpenAI vs Gemini vs Claude structured-output benchmark) | All team members | Before Week 3 | Mandatory for JD domain owners |
| PDF text extraction (spike SPK-01: pdfcpu vs ledongthuc/pdf vs pdftotext) | All team members | Before Week 3 | Mandatory for JD domain owners |
| Web-based 3D avatar and lip-sync (spike SPK-03: viseme morph-target interpolation) | All team members | Before Week 5 | Mandatory for Avatar/Audio owners |
| Third-party payment gateway integration (VNPay / MoMo / Stripe / PayOS) | All team members | Before Week 7 | Mandatory for Payment domain owners |

## 3. Project Deliverables

The following deliverables follow the SEP490 Student Guide milestone table. Dates are planning displays based on a Week 1 start of 07/09/2026.

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Report 1 — Project Introduction | 11/09/2026 | Week 1 planning display |
| 2 | Report 2 — Project Management Plan | 18/09/2026 | Week 2 planning display |
| 3 | Initial Report 3 — Software Requirement Specification baseline | 25/09/2026 | Week 3 planning display; update Reports 1–2 and project tracking |
| 4 | Initial Report 4 and Report 5 materials; code frame | 09/10/2026 | Week 5 planning display |
| 5 | Software Package 1 | 23/10/2026 | Week 7 planning display |
| 6 | Software Package 2 | 06/11/2026 | Week 9 planning display |
| 7 | Software Package 3 | 20/11/2026 | Week 11 planning display |
| 8 | Full Software Package | 04/12/2026 | Week 13 planning display |
| 9 | Report 6 — Software User Guides | 11/12/2026 | Week 14 planning display |
| 10 | Report 7, final project products, and presentation file | 18/12/2026 | Week 15 planning display |

## 4. Responsibility Assignments

D~Do; R~Review; S~Support; I~Informed; <blank>- Omitted.

| Responsibility | BaoTC SE190084 | KhangHM SE192197 | AnhNHN SE190291 | NamDP SE192107 | TrongNT SE190353 |
| --- | --- | --- | --- | --- | --- |
| Project Planning & Tracking |  |  | D |  |  |
| Prepare Project Introduction Document | R | R | R | D | R |
| Prepare Project Management Plan | R | R | R | R | D |
| Prepare Software Requirement Specification | R | R | D | R | R |
| Prepare Design, Test, and User Guide artefacts |  |  |  |  |  |
| Implementation, integration, and deployment activities |  |  |  |  |  |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Supervisor meeting | Supervisor and team | Progress review and guidance | As arranged | Offline - University Online - Google Meet |
| Team coordination | Project team | Work coordination and review | As arranged | Discord (tentative — confirm with team) |
| Weekly project report | Team and supervisor | Status, issues, and next-week plan | Weekly | Project Weekly Report template (SEP490) |
| Project tracking | Project team | Issues, defects, and Q&A | As arranged | Jira (board "KAN") |

## 6. Configuration Management

### 6.1 Document Management

University report templates (Reports 1–7) and submitted source files remain unchanged. Working documents are version-controlled through Git/GitHub within a structured project knowledge base (numbered folder taxonomy: Control Center, Contracts, Decisions, Domains, Execution, Codebase, Meetings, Research Spikes, Reports, Legacy Reference, Inbox). Each technical or product decision is recorded in a central Decision Registry with an explicit authority hierarchy (accepted ADR > Jira acceptance criteria > merged code > meeting decisions > requirements/register > legacy/speculative specs) and dated Sync-Log entries. Report versions use a vN.N naming convention (e.g. Report2_Project_Management_Plan_v0.2.docx) with a Record of Changes table in each document.

Final review, approval, and sharing workflow: TBD — Team confirmation.

### 6.2 Source Code Management

GitHub is the source code management platform.

- Repository: github.com/swp391-group3/ai-interview-practice (monorepo: api/ Go backend, frontend/ Next.js client).

- Workflow: feature branch → Pull Request → mandatory review → merge into main, already applied in practice (PR #1–#15).

- Branch naming convention: feature/*, chore/*.

- Database schema changes use numbered golang-migrate SQL migrations (.up.sql / .down.sql).

Access control, release tagging, and issue-management conventions: TBD — Team confirmation.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Server-side technology | Go 1.27, Gin, Viper (config), Zap (logging), OpenTelemetry (tracing), Wire (DI) |
| Database | PostgreSQL, accessed via pgx/v5 and sqlc; schema versioned with golang-migrate |
| Web client | Next.js 16, React 19, Bun, Tailwind CSS v4, shadcn/ui, TanStack Query, Zustand, React Hook Form + Zod, Three.js / @react-three/fiber |
| AI integration | Large Language Model APIs via Eino (current adapter: Google Gemini) for JD analysis, interview generation, follow-up questioning, and evaluation |
| Voice interaction | Speech-to-Text and Text-to-Speech services — provider open (candidates: Whisper/Deepgram for STT; ElevenLabs/Azure Speech for TTS) |
| Payment integration | Third-party payment gateway — provider open (candidates: VNPay, MoMo, Stripe, PayOS) |
| Source code management | GitHub — github.com/swp391-group3/ai-interview-practice |
| Testing | Go testing, Vitest, Playwright, Testcontainers |
| Diagramming | draw.io, Mermaid |
| Documentation & project tracking | Git-based project knowledge base; Jira (board "KAN") |
| Team communication | Discord (tentative — confirm with team) |
| Deployment infrastructure | TBD — Team confirmation |